LAND STACK

Report 4: Officer Dashboard, Workflow, Security and Audit

Full-Stack track, Member 4

| Item | Detail |
| --- | --- |
| Project | Land Stack: Integrated GIS-Based Digital Public Infrastructure for Land Governance |
| Team member | Member 4 (Full-Stack) |
| Role | Officer Dashboard, Workflow, Security and Audit |
| Nature | Applied Research + Software Development + GIS-Based Prototype |
| Current TRL / target | TRL 2 / TRL 4 |
| Duration | 18 weeks |

# 1. Role Overview

Member 4 builds the governance layer: who can log in, what each role can see and do, how approvals move through departments, how every action is recorded, and the dashboards officers use to manage land information. This makes the platform accountable and auditable.

## 1.1 Position in the project

Users (citizen, officers, admin) --> [ Auth + RBAC ] --> [ Workflow engine ] --> [ Audit log ]

|                    |

Officer Dashboard      Events to/from Member 2 APIs

# 2. Objectives

- Implement secure authentication and role-based authorization.

- Define roles and permissions for citizens, revenue, registration, municipal and planning officers, and administrators.

- Build workflows for mutation, permission approval and service requests.

- Record an immutable audit trail of data access and changes.

- Build officer dashboards with statistics, API status and AI alert review.

# 3. Scope

## 3.1 In scope

- Login, tokens, session security

- RBAC policy and enforcement

- Workflow engine and state machines

- Audit logging and viewer

- Officer dashboards

- Security testing

## 3.2 Out of scope

- Citizen map UI (Member 1)

- Business APIs and schema mapper (Member 2)

- Infrastructure security such as WAF and network policy (Member 6)

# 4. Technology Stack

| Area | Tools / Technology | Purpose |
| --- | --- | --- |
| Identity | Keycloak (OAuth2 / OpenID Connect) | Login, tokens, roles |
| Authorization | Role and attribute checks in middleware | RBAC enforcement |
| Workflow | State-machine library or Camunda/Temporal (lightweight option: custom) | Approval flows |
| Audit | Append-only table with hash chaining | Tamper-evident log |
| Frontend | React + TypeScript, charting library | Officer dashboards |
| Security testing | OWASP ZAP, dependency scanning | Vulnerability checks |

# 5. Modules and Deliverables

| Module | Description | Output |
| --- | --- | --- |
| Authentication | OIDC login, token refresh, logout, password policy | Auth service and login screens |
| RBAC | Role matrix and middleware to enforce it | Role and permission specification |
| Workflow engine | Mutation, building-permission and service-request flows with states and SLAs | Workflow definitions |
| Audit trail | Who, what, when, from where for every read of sensitive data and every change | Audit service and viewer |
| Officer dashboard | Parcel counts, pending tasks, tax dues, AI alerts, API health | Dashboard screens |
| Notifications | Status updates for requests and approvals | Notification module |

## 5.1 Proposed roles

- Citizen: view own and public parcel information, submit requests

- Revenue officer: verify RoR, approve mutation

- Registrar: verify registration and encumbrance data

- Municipal officer: building permission and property tax

- Planner: land-use and zoning views, AI alert review

- Administrator: users, roles, system configuration, audit viewing

## 5.2 Sample mutation workflow

Registration recorded, then mutation request created, then revenue officer verification, then approval or rejection with reason, then RoR updated and citizen notified. Every step writes an audit event.

# 6. Datasets Used

| Dataset | How it is used in this role |
| --- | --- |
| Synthetic user and role data | Test accounts for each role |
| Synthetic departmental records | Workflow inputs such as pending mutations and permits |
| AI alerts from Member 5 | Shown in dashboard for officer verification |

# 7. Interfaces with Other Team Members

| With | This role provides | This role needs |
| --- | --- | --- |
| Member 1 (Frontend) | Login flow, tokens, roles, shared UI components | Design system and layout |
| Member 2 (Backend) | Auth middleware, audit event format, workflow hooks | Endpoints emitting events |
| Member 3 (Database) | Workflow and audit table requirements | Tables and indexes |
| Member 5 (AI/ML) | Alert review and feedback screens | Alert data with confidence scores |
| Member 6 (Cloud) | Identity provider deployment needs | Secrets management, TLS, hosting |

# 8. Work Plan

| Phase | Weeks | Tasks |
| --- | --- | --- |
| Design | 4-6 | Role matrix, workflow diagrams, audit event schema, dashboard wireframes |
| Auth | 7-9 | Identity provider setup, login, RBAC middleware |
| Workflow and audit | 9-12 | Workflow engine, audit trail, notifications |
| Dashboard | 10-13 | Officer dashboards and alert review UI |
| Security testing | 14-16 | OWASP checks, permission tests, audit integrity tests |
| Document | 17-18 | Security and authorization guide, admin manual |

# 9. Acceptance Criteria

- Each role can access only what the role matrix allows, verified by automated tests.

- All sensitive reads and every data change produce an audit record.

- Audit records are tamper-evident and cannot be edited through the application.

- Mutation and permission workflows run end to end.

- Security scan shows no unresolved high-severity issues.

# 10. Risks and Mitigation

| Risk | Mitigation |
| --- | --- |
| Over-complex workflow tooling | Start with simple state machines, upgrade only if needed |
| Permission gaps | Permission tests for every endpoint and role |
| Audit log growth | Partitioning and retention policy |

# 11. Contribution to Project Goals

This module makes the platform trustworthy. It supports SDG 16.6 (accountable institutions), SDG 16.5 (reducing corruption through visible, audited processes) and SDG 16.3 (reliable records that reduce disputes).

# 12. Skills and Learning Outcomes

- OAuth2/OIDC and RBAC

- Workflow design

- Audit and security engineering

- Dashboard design

# References

- PIB (May 2026), Land Stack Initiative to Usher in Transparent and Citizen-Centric Land Management. https://www.pib.gov.in/PressReleasePage.aspx?PRID=2259050

- PIB (Dec 2025), National Symposium on Naksha and LandStack. https://www.pib.gov.in/PressReleasePage.aspx?PRID=2197439

- PIB (Sept 2026), Operational Guidelines for DILRMP 3.0. https://www.pib.gov.in/PressReleaseIframePage.aspx?PRID=2308504

- PIB (May 2026), Land Stack as next layer of Digital Public Infrastructure. https://www.pib.gov.in/PressReleasePage.aspx?PRID=2263740

- PIB (Aug 2026), Bharat Land Stack and Bhu-Aadhaar. https://www.pib.gov.in/PressReleasePage.aspx?PRID=2303882

- DoLR, DILRMP / ULPIN page. https://dolr.gov.in/en/department-of-land-resources-govt-of-india-is-implementing-digital-india-land-records-modernization-program-through-state-ut-governments/